## Φύλλο1
| 2021-06-01 |  |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  |  | 2021-11-01 |  |  |  | 2021-12-01
| 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Preparation Phase | bar: 2021-05-31 to 2021-07-05
Literature review on NLP (stemming/lemmatising) | bar: 2021-05-31 to 2021-07-05
Literature review on converting text to vectors | bar: 2021-05-31 to 2021-07-05
Literature review on classification for KG embeddings | bar: 2021-05-31 to 2021-07-05
Set a programming environment | bar: 2021-06-28
Design Phase | bar: 2021-07-05 to 2021-09-13
Text Processing Feature | bar: 2021-07-05
Integrate with KB to lookup entities extract classes | bar: 2021-07-12
Design Classifier | bar: 2021-07-19 to 2021-07-26
Design a solution for CEA | bar: 2021-08-30 to 2021-09-06
Design a solution for CPA | bar: 2021-09-06 to 2021-09-13
Implementation Phase | bar: 2021-07-12 to 2021-10-25
Implement Text Processing Feature | bar: 2021-07-12 to 2021-07-26
Implement KB Integration | 2021-09-13: MVP
Implement Classification for CTA | bar: 2021-07-26 to 2021-08-16
Test and Experiment run | bar: 2021-08-16 to 2021-09-06
Experiment with other KGs | bar: 2021-08-30 to 2021-09-13
Implement CEA | bar: 2021-09-13 to 2021-09-27
Implement CPA | bar: 2021-09-27 to 2021-10-11
Additional experimentation for CEA and CPA | bar: 2021-10-11 to 2021-10-25
Code Refactoring | bar: 2021-09-13 to 2021-10-25
Reporting | bar: 2021-10-11 to 2021-12-20
Write up initial Draft | bar: 2021-10-11 to 2021-11-22
Send for review | bar: 2021-11-29
Incorporate review feedback | bar: 2021-12-06 to 2021-12-13
Submit thesis | bar: 2021-12-20